## Bug Reports
Name of the Application | Swag Labs (SauceDemo)
URL | https://www.saucedemo.com/
Browser Version | Chrome 130.0.6723.59 (64-bit)
Tester | Taffazul Ansari
Date | 2026-10-06
Approved By | Sauce Demo
Bug ID | Test Case ID | Module/Area | Description | Steps to Reproduce | Expected Result | Actual Result | Severity | Priority | Status | Screenshots/Video
BUG_001 | TC_001 | Dynamic Catalog > Lazy Load | The product list continues loading indefinitely while scrolling down the page. | 1. Log in to the website. 2. Navigate to Dynamic Catalog > Lazy Load. 3. Scroll down continuously. 4. Observe the product list and loading behavior. | Products should load according to the defined pagination or lazy-loading limit, and a proper end-of-list indicator should appear when applicable. | Products continue appearing or loading indefinitely, with no clear end to the list. | Medium | Medium | Fail | http://srecorder.com/s/1evn1
BUG_002 | TC_002 | Authentication – Login/Logout | Toast notification messages are missing after successful login and logout. | 1. Open the login page. 2. Enter valid credentials and log in. 3. Observe the notification area. 4. Log out and observe the notification area again. | A suitable success toast message should appear after successful login and logout, if specified by the application requirements. | No toast notification is displayed after login or logout. | Low | Medium | Fail | http://srecorder.com/s/1evn2
BUG_003 | TC_003 | Application State – Reset App State | The Reset App State button does not reset the application to its initial state. | 1. Log in to the website. 2. Modify the application state, such as adding products to the cart. 3. Click Reset App State. 4. Verify the cart and other resettable application data. | The application should reset the relevant state according to the button's intended functionality. | Clicking Reset App State does not produce the expected reset behavior. | High | High | Fail | http://srecorder.com/s/1evn5
BUG_004 | TC_004 | UI/UX – Overall Website | The website UI appears incomplete, with some interface elements or layouts missing or improperly rendered. | 1. Open the website. 2. Navigate through the available pages and modules. 3. Inspect page layouts, controls, labels, buttons, and alignment. | All pages should display complete UI elements with consistent styling, alignment, and usability. | Some UI elements or layout components appear incomplete or improperly rendered. | Medium | High | Fail | http://srecorder.com/s/1evn7
BUG_005 | TC_005 | Dynamic Catalog > Lazy Load – Add to Cart | Users are unable to add products to the cart from the Lazy Load page and others. | 1. Log in to the website. 2. Navigate to Dynamic Catalog > Lazy Load and others. 3. Locate a product. 4. Attempt to add it to the cart. 5. Verify the cart contents. | Users should be able to add eligible products to the cart, and the cart count should update accordingly. | Products cannot be added to the cart from the Lazy Load page and others. | High | High | Fail | http://srecorder.com/s/1evn8
BUG_006 | TC_006 | Product Listing – Add to Cart Button | Add to Cart buttons are missing from product listings. | 1. Log in to the website. 2. Navigate to the product listing pages. 3. Inspect the available product cards. | Each eligible product card should display an accessible Add to Cart button. | Add to Cart buttons are missing from the product listings. | High | High | Fail
BUG_007 | TC_007 | Navigation – Back Button | The Back button is missing from pages where users need to return to the previous page or step. | 1. Navigate through the website to a nested page or workflow. 2. Inspect the page for a Back button. 3. Attempt to return to the previous step. | A Back button should be available wherever required by the application's navigation design and should return users to the previous step. | The Back button is missing from the affected page or workflow. | Medium | Medium | Fail | http://srecorder.com/s/1evn6
BUG_008 | TC_008 | Product Listing – Quantity Management | Users are unable to increase or decrease the quantity of a product. | 1. Log in to the website. 2. Navigate to a product listing or cart page. 3. Select a product. 4. Attempt to increase or decrease its quantity. 5. Verify the quantity and price totals. | Users should be able to adjust product quantities where supported, and the cart quantity and price totals should update correctly. | The product quantity cannot be increased or decreased. | Medium | High | Fail
BUG_009 | TC_009 | Dynamic Catalog > Lazy Load > Spinner > Slider | Clicking the Slider option redirects the user to the login page unexpectedly. | 1. Open the website. 2. Navigate to Dynamic Catalog. 3. Open Lazy Load. 4. Navigate through Spinner to Slider. 5. Click Slider. | The Slider page should open successfully without redirecting the user to the login page. | The user is redirected to the login page after clicking Slider. | High | High | Fail | http://srecorder.com/s/1evn9
Bug_010 | TC_010 | Checkout > Your Information > Overview | Checkout information entered on the Your Information page is not displayed on the Checkout: Overview page. | 1. Log in to Swag Labs. 2. Add products to the cart. 3. Navigate to Checkout. 4. Fill in the required information. 5. Click Continue. 6. Verify the Checkout: Overview page. | The entered checkout information should be displayed on the Overview page if required by the application requirements. | The previously entered checkout information is not displayed on the Checkout: Overview page. | Low | Medium | Fail | http://srecorder.com/s/1evna